## Back-End
Backlog | Status | Contributor
1.) Create a CookieHandler class for user information across client-server code. | Pending
Will handle getters and setters of cookie-based information of the user | Pending
2.) Create an ASP.NET Core solution | DONE | Rex
3.) Create an Entity and Dynamic Renderer for Web Links | DONE | Rex
4.) Create an Entity List Dynamic Renderer | Pending
5.) Create an Entity Form Dynamic Renderer | Pending
6.) Create a View Component for Lookups | Pending
7.) Create a View Component for Entity/List and SubGrid | Pending
8.) User Must Be Able to Login in with different Identity Providers(Database,Service,CRM). | DONE | Rex
9.) Administrator must be able to maintain User Entity | In Progress | Rex
10.) Administrator must be able to maintain Roles Entity | Pending
11.) Administrator must be able to maintain Web Links Entity | Pending
12.) Create a generic RESTful Service for Entity Lists with minimal performance drawback | Pending
12.) Create a generic RESTful Service for Creating an Entity with minimal performance drawback | Pending
12.) Create a generic RESTful Service for Updating an Entity with minimal performance drawback | Pending
12.) Create a generic RESTful Service for Deleting an Entity with minimal performance drawback | Pending

## UI-UX
Backlog | Status | Contributor
There should be a template for Login | DONE | Rex
There should be a template for User Profile | Pending
There should be a template for Navigation | Pending
There should be a template for Entity List | DONE | Rex
There should be a template for Entity Form | DONE | Rex
There should be a template for Toolbar | DONE | Rex
There should be a template for Footer | DONE | Rex
There should be a template for Header | DONE | Rex
There should be a template for Progress Bar (youtube like). | Pending
There should be a template for Notification or Alerts (floating). | Pending
There should be a template for 404 request result (user friendly) | Pending
There should be a template for 500 request result for Development Environment (dev friendly) | Pending
There should be a template for 500 request result for Production Environment (user friendly) | Pending
There should be a template for Lookups | Pending
There should be a template for OptionSet | Pending
There should be a template for Currency | Pending
There should be a template for Date and Time | Pending
There should be a template for Quick Create Forms (Maintenance Forms. Max of 5 fields). | Pending
There should be a template for Medium Form (Child Form). | Pending
There should be a template for Subgrids (Partial Rendering). | Pending