## Sheet1
Backlog | Status
1.) Create a CookieHandler class for user information across client-server code. | Pending
Will handle getters and setters of cookie-based information of the user | Pending
2.) Create an ASP.NET Core solution | DONE
3.) Create an Entity and Dynamic Renderer for Web Links | Pending
4.) Create an Entity List Dynamic Renderer | Pending
5.) Create an Entity Form Dynamic Renderer | Pending
6.) User Must Be Able to Login in with different Identity Providers(Database,Service,CRM). | In Progress
7.) Create a UI Template for the MVC app solution | In Progress
There should be a template for Login | DONE
There should be a template for User Profile | Pending
There should be a template for Navigation | Pending
There should be a template for Entity List | DONE
There should be a template for Entity Form | DONE
There should be a template for Toolbar | DONE
There should be a template for Footer | DONE
There should be a template for Header | DONE
There should be a template for Progress Bar (youtube like). | Pending
There should be a template for Notification or Alerts (floating). | Pending
There should be a template for 404 request result (user friendly) | Pending
There should be a template for 500 request result for Development Environment (dev friendly) | Pending
There should be a template for 500 request result for Production Environment (user friendly) | Pending
There should be a template for Lookups | Pending
There should be a template for OptionSet | Pending
There should be a template for Currency | Pending
There should be a template for Date and Time | Pending
There should be a template for Quick Create Forms (Maintenance Forms. Max of 5 fields). | Pending
There should be a template for Medium Form (Child Form). | Pending
There should be a template for Subgrids (Partial Rendering). | Pending